## Sheet1
Team Member | Deliverable | Schedule | Client | Priority | Means of Communication | Bite-Sized Updates
Project Manager | Project Status Reports | Weekly (Every Friday) | Mall Management | High | Email, Project Management Software | Weekly status updates, key milestones
IT Specialists | System Integration Updates | Bi-Weekly | Mall Management, Technology Vendors | High | Email, Meetings | Integration progress, issues, resolutions
Electrical Engineers | Electrical System Progress | Monthly | Mall Management, Installation Contractors | Medium | Email, Meetings | Electrical system updates, any delays
Security Experts | Security System Installation | Monthly | Mall Management | High | Email, Meetings | Security installation progress, testing results
Data Analysts | Data Analytics Reports | Monthly | Mall Management, Marketing Specialists | Medium | Email, Project Management Software | Data insights, trends, and recommendations
App Developers | App Development Milestones | Bi-Weekly | Mall Management | High | Email, Project Management Software | Development progress, beta testing feedback
Robotics Engineers | Robotics Deployment Progress | Monthly | Mall Management | Medium | Email, Meetings | Deployment status, testing outcomes
Installation Contractors | Installation Progress Updates | Weekly | Mall Management, Electrical Engineers | High | Email, Meetings | Installation status, any site issues
Maintenance Staff | Maintenance Status Reports | Monthly | Mall Management | Medium | Email, Project Management Software | Maintenance updates, scheduled tasks
Customer Support | Customer Service Training | As Needed | Mall Management, Training Specialists | High | Email, Meetings, Workshops | Training progress, feedback from sessions
Training Specialists | Training Materials & Sessions | As Needed | Mall Management, Customer Support | High | Email, Workshops | Training schedules, materials updates
Marketing Specialists | Marketing Campaign Status | Bi-Weekly | Mall Management, Marketing Team | Medium | Email, Meetings | Campaign progress, performance metrics
Communications Team | Communication Materials | Monthly | Mall Management, Marketing Team | Medium | Email, Meetings | Updates on communication materials, strategies
Technology Vendors | Equipment Delivery Updates | As Needed | Mall Management | High | Email, Phone Calls | Delivery status, any issues
Consultants | Expert Advice & Recommendations | As Needed | Mall Management | Medium | Email, Meetings | Consultant feedback, recommendations
Contractors | Construction Progress | Weekly | Mall Management | High | Email, Meetings | Construction updates, any delays
Contingency Fund Manager | Budget Adjustments | As Needed | Mall Management | Medium | Email, Project Management Software | Budget status, any changes