## Sheet1
Risk | Type | Description | Probability | Impact | Severity | Response Plan
Technology Failures | Operational | Malfunctions in smart systems such as HVAC, lighting, etc. | High | High | Critical | Implement robust testing, maintenance, and backup systems.
Cybersecurity Threats | Security | Risks of data breaches or cyberattacks. | Medium | High | High | Use advanced security measures, conduct regular vulnerability assessments.
Vendor Reliability | Strategic | Issues with third-party vendors' performance. | Medium | Medium | Medium | Establish contracts with clear SLAs and maintain strong vendor relationships.
Integration Challenges | Technical | Difficulties integrating new smart technology with existing systems. | High | Medium | High | Conduct thorough planning and testing to ensure smooth integration.
Compliance Issues | Compliance | Non-compliance with regulations and standards. | Low | High | Medium | Stay informed on regulations and ensure compliance through regular audits.
Cost Overruns | Financial | Unforeseen expenses exceeding the budget. | Medium | High | High | Develop a detailed budget with contingencies and monitor expenditures closely.
Electricity Outage | Operational | Power loss affecting all smart systems and building operations. | Medium | High | High | Install backup generators and uninterruptible power supplies (UPS); develop an outage response plan.