## Resource Plan Template
Timeless Mall Resource Plan
Project Name | Project Manager | Client | Date
TimeLess Mall | NTI | Timeless smart mall | 2024-11-09
Resource | Team | Total Effort | Rate | Cost | Jan | Feb | Mar | April | May | May | June | July | Aug | Sep | Oct | Nov | Dec
Project Manager | Project Management | 500 | 100 | 50000 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
IT Specialists | Technical Team | 1000 | 80 | 80000 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Electrical Engineers | Technical Team | 800 | 90 | 72000 | April: 200; May: 200; May: 200; June: 200
Security Experts | Technical Team | 600 | 85 | 51000 | May: 200; May: 200; June: 200
Data Analysts | Technical Team | 400 | 75 | 30000 | May: 80; May: 80; June: 80; July: 80
App Developers | Technical Team | 500 | 100 | 50000 | May: 100; May: 100; June: 100; July: 100; Aug: 100
Robotics Engineers | Technical Team | 400 | 95 | 38000 | May: 100; May: 100; June: 100; July: 100
Installation Contractors | Installation & Maintenance | 1200 | 70 | 84000 | May: 300; June: 300; July: 300; Aug: 300
Maintenance Staff | Installation & Maintenance | 600 | 60 | 36000 | June: 150; July: 150; Aug: 150
Customer Support | Support & Training | 300 | 50 | 15000 | Aug: 75; Sep: 75
Training Specialists | Support & Training | 250 | 55 | 13750 | Aug: 50; Sep: 50
Marketing Specialists | Marketing & Communications | 400 | 70 | 28000 | June: 100; July: 100; Aug: 100; Sep: 100; Oct: 100
Communications Team | Marketing & Communications | 200 | 65 | 13000 | June: 50; July: 50; Aug: 50; Sep: 50
Technology Vendors | External Resources | - | - | 1200000 |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Consultants | External Resources | - | - | 200000 | Aug: 50000; Sep: 50000; Oct: 50000
Contractors | External Resources | - | - | 500000 | May: 100000; June: 100000; July: 100000; Aug: 100000; Sep: 100000
Contingency Fund | - | - | - | 200000